## Active
Id | Title | Status | Category | Created
49 | update to only open/create/save new xml format | Todo | Feature | 9/12/2018
58 | refactor: Task.Title is being used as full task description, so update the property name and the excel column name - breaking change so wil lneed new version number | Todo | Feature | 9/13/2018
47 | broke the icon again | Todo | Bug | 9/12/2018
51 | update license | Todo | Documentation | 9/12/2018
50 | cleanup documentation make it consistent with library projects | Todo | Documentation | 9/12/2018
46 | convert dev_notes.txt to this todo list | Todo | Documentation | 9/12/2018
53 | github use case: user1 adds a task, given id 5 user2 at the same time adds a task, given id 5 both users check in github merges the files now there are two tasks with id 5 What validation and auto-update should Tamarin do when it next opens the file? this will certainly need to be documented behavior | Todo | Feature | 9/13/2018
39 | go through Lia's test results | Todo | Task | 4/11/2018
54 | create a custom layout manager that works better and faster - at the same time, refactor all forms from Design to Code | Todo | Task | 9/13/2018
40 | don't leave comboboxes highlighted in blue after the list is updated | Todo | Task | 4/11/2018
2 | when first switching to pre-loaded tab, pause layout until visuals are ready | Todo | Bug | 10/28/2017
33 | I think fixing the lingering layout/scrolling issues will require a massive redesign of the gui layout system maybe in version 3 | Todo | Bug | 4/11/2018
34 | visual indication that a list has been edited but not saved | Todo | Feature | 4/11/2018
38 | better icon | Todo | Feature | 4/11/2018
41 | when adding new task to Inactive list directly, auto-select the first inactive status possible | Todo | Bug | 4/11/2018
42 | don't let user save with any file format suffix other than xlsx - was able to save with filename x.txt | Todo | Bug | 8/9/2018
43 | probably need to roll my own layout manager it takes WAY too long to switch lists, open lists, close lists | Todo | Bug | 8/9/2018
52 | if only an empty "new" file is open, and user opens an actual file, then auto-close the empty file | Todo | Bug | 9/12/2018
13 | make it more obvious which tab is selected - with color or by removing the border between tab and pane | Todo | Feature | 12/14/2017
30 | you can move a row to a row higher than you should be able to | Todo | Bug | 4/11/2018
31 | adding a task with Add Button does not set task height properly | Todo | Bug | 4/11/2018

## Inactive
Id | Title | Status | Category | Created | Done
57 | major refactor step 3: save generic Project format to xml on save, if filename has xlsx extension, auto save it to filename.xml instead | Done | Feature | 9/13/2018 | 9/13/2018
56 | major refactor step 2: load excel format into generic Project format don't keep the excel objects all edits must be made to generic Project objects | Done | Feature | 9/13/2018 | 9/13/2018
55 | major refactor step 1: on save, write the entire excel worksheets at once | Done | Feature | 9/13/2018 | 9/13/2018
45 | FOUND MAJOR FLAW IN DESIGN: xlsx files can't merge in Git, at least not in any meaningful way can I save to pure xml instead? that should merge ok I can at least read it in Notepad Yes, can save to MS Excel 2003 XML format - verified OpenOffice can open that | Done | Feature | 9/12/2018 | 9/12/2018
44 | rename repository to Tamarin | Done | Feature | 9/12/2018 | 9/12/2018
22 | get the msi installed program to run again - it won't run after installation UPDATE the problem was that I manually set the WindowsForm icon file in the code and the file could not be found took that out since I set the icon file through project properties runs fine now | Done | Bug | 3/2/2018 | 4/11/2018
5 | if category A is removed, and category B is added, and category A is a starting-sub-string of B then all category A tasks are auto reset to B - they should not be | Done | Bug | 12/1/2017 | 4/11/2018
29 | editing statuses or categories does not prompt a Save when you close | Done | Feature | 4/11/2018 | 4/11/2018
35 | ctrl-up/down arrow to jump from task to task, instead of through the lines of a task | Done | Bug | 4/11/2018 | 4/11/2018
32 | when moving a row, move cursor to the row that is now in the position that the moved row previously held | Done | Bug | 4/11/2018 | 4/11/2018
26 | enter in row number field should accept the edit | Done | Feature | 4/10/2018 | 4/11/2018
17 | option to clear inactive list | Done | Feature | 12/18/2017 | 4/11/2018
28 | on Load Previous Projects - auto select first project in list instead of last | Done | Bug | 4/10/2018 | 4/11/2018
19 | if there are zero or one Category options total, then hide category column on both pages | Done | Feature | 1/7/2018 | 4/11/2018
27 | changing between active and inactive - need a reminder to the program to update titleBox sizes and UpdateTextBoxSizes does not help - UPDATE now it does only affects some titles | Done | Bug | 4/10/2018 | 4/11/2018
24 | the scroll bar is way way longer than the content something about the SizeChanged aspect of the titleBox UPDATE: the table height is getting set to the height needed if textboxes are as narrow as they are allowed to be, plus one extra page height got this as short as possible - it used to be way way taller than that acceptable | Done | Bug | 4/10/2018 | 4/11/2018
25 | scrolling with mouse wheel only works on a small part of the screen | Done | Bug | 4/10/2018 | 4/10/2018
15 | only allow one instance of this program open at a time | Skip | Feature | 12/15/2017 | 3/5/2018
14 | notify if file was changed by another program - or another instance of this program - reload or overwrite | Done | Bug | 12/15/2017 | 3/5/2018
12 | warn when closing with unsaved data | Done | Bug | 12/8/2017 | 3/5/2018
18 | have as little border space between elements as possible | Done | Feature | 12/19/2017 | 3/3/2018
16 | size text areas so no scrolling is ever needed - always apply scrolling to the whole pane, not to any of the inputs | Done | Feature | 12/15/2017 | 3/3/2018
11 | when click + (add task) button, and new task is below scroll viewable area, should auto scoll to focus on new task | Done | Bug | 12/7/2017 | 3/3/2018
8 | when new task is created, default set its drop downs to the same values as the one above it | Done | Feature | 12/1/2017 | 3/3/2018
23 | when combox value is changed, return focus to textbox | Done | Feature | 3/3/2018 | 3/3/2018
10 | icon for program | Done | Feature | 12/5/2017 | 3/3/2018
9 | deactivate mouse scroll when hovering over dropdowns i accidently set 5 rows to Done with one scroll | Done | Bug | 12/1/2017 | 3/3/2018
7 | down-arrow from last line of text should move into next text box and up-arrow should move to previous field | Done | Feature | 12/1/2017 | 3/3/2018
6 | tabbing from text should move to next text, not the drop downs | Done | Feature | 12/1/2017 | 3/3/2018
4 | have some key command to end the current task and immediately open and edit a new task below it Ctrl-N (Next or New) | Done | Feature | 12/1/2017 | 3/3/2018
21 | Have executable be named Tamarin.exe to match installation program name -update installer to Tamarin | Done | Feature | 3/2/2018 | 3/3/2018
1 | line wrap long descriptions and increase textbox height to accomodate | Done | Bug | 10/27/2017 | 3/2/2018
3 | program icon | Done | Feature | 10/28/2017 | 2/26/2018

## Config
Status | Active | Category | Max Id
Todo | Active | Feature | 58
Pending | Active | Task
Done | Inactive | Bug
Skip | Inactive | Documentation